## SAMS
Iteration1, 4 wks 09/12/2021- 10/11/2021 | Iteration2, 4 wks 10/12/2021- 11/11/2021 | Iteration2, 4 wks 10/12/2021- 11/11/2021
UC 1: Do One points: 4 priority: 1 Depends on: None | UC 4: Do Four points: 1 priority: 1 Depends on: None | UC 8: Do Eight points: 6 priority: 1 Depends on: UC 3
Assumptions: (1) The team can produce 3 points of work per week. (2) Priorities are ranked from 1 to 4, with 1 being the highest.
UC2: Do two points: 2 priority: 2 Depends on: UC1 | UC 6: Do Six points: 5 priority: 3 Depends on: UC 3 | UC 9: Do Nine points: 5 priority: 2 Depends on: UC 3, UC 8
UC 3: Do three points: 5 priority: 1 Depends on: UC 1, UC 2 | UC 7: Do Seven points: 3 priority: 4 Depends on: UC3, UC 6
UC 5: Do Five points: 1 priority: 4 Depends on: UC 4

## Risk
Risks | Risk Resolution Measures | Justification
1. Student can forget their username or password for login. | Contact with the admin to restore uername and password | To restore the username and password, user can contact the admin to restore their username and password
2. Personnal shortfalls | Staffing with top talent, job matching, key personnel agreements | To avoid staff shortfall, management should hire the person who is capabale of the position and provide the agreement.
3. Student applying for the incorrect subject or semester | Reverify the application | To avoid the mistake in application, student and management to verify all the information in the application before approving.
4. College website going under maintenance | Maintain the website during off hours | In order for all the staff and student to get work done, all the website maintenance should be done during off hours.
5. Application filled out incorrectly | Reverify all the documents | Sometimes student might put some information incorrect, so in order to verify that, all the proper document should be uploaded with application.